## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2221-SWEN-261-05-F-FantasticFive
User Story | Acceptance Criteria | Pass/Fail
Testing Team Name

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page.
Given that I am not on the Products page when I choose the Products page then I am taken to the Products page.
Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available.
Given that I am on the products page when there are products in the inventory then I see each product and short description.
Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart.
Owner, Browse Products | **Given** This is a logged in owner **when** I view the current campsites **then** I expect to see the price, name , and id number | Pass | Sherry Robinson, 11/2/2022
User Login | **Given** Owner has an account **when**Owner enters correct login credentials **then** owner can access E-store with owner privileges. | Pass | Troy Wolf, 11/2/22
| **Given** Customer has an account **when**Customer enters correct login credentials **then** customer can access E-store. | Pass | Michael Oldziej, 11/2/22
| **Given** This is a logged in owner **when** I view the current campsites **then** I expect to see the price, name , and id number | Pass | Sherry Robinson, 11/2/22
Owner Remove Campsite | **Given** I am logged in as an admin **when** I view a campsite and know that it is not available any more **then** I expect to be able to remove a campsite from the availability map | Pass | Troy Wolf, 11/2/22
Buyer Search Campsite | **Given** I am logged in as a user, **when** I want to search for an item**then** I expect to be able to use a search bar to find any campsites that I want | Pass | Michael Oldziej, 11/2/22
Buyer See Purchased Reservations | **Given** the user has logged in **when** they select "Reservations" **then** a list of their paid reservations will be shown. | Pass | Sherry Robinson, 11/2/22
Buyer, Checkout | **Given** I am a user and there are products in the shopping cart **when** I select the checkout feature **then** I am given an overview of my selected products and the option to purchase them. | Pass | Kolbe Yang, 11/2/22
Buyer, Cancel Reservation | **Given** I'm a valid user **when** I have an active reservation **then** I EXPECT to be able to cancel/ remove the reservation prior to it occurring from the My Reservations page. | Pass | Lianna Pottgen, 11/2/22
Buyer, Select Campsite | **Given** I am a valid user **when** I select a campsite from list**then** I EXPECT to be able to see the associated information and rent the campsite if it's available. | Pass | Lianna Pottgen, 11/2/22
Buyer, Add Reservation to Cart | **Given** I have logged in **when** I choose a time and place for my reservation and add it to my cart **then** I expect my spot at that campsite will be reserved. | Pass | Kolbe Yang, 11/2/22
| **Given** There are reservations for a campsite **when** I choose a time for a reservation that conflicts with a previous time **then** I expect my reservation to be rejected. | Pass | Kolbe Yang, 11/2/22
Owner, Add Campsite | **Given** I'm logged in as owner **when** I add a campsite **then** I EXPECT the customers to be able to view the new campsite on the map, and view the associated information. | Pass | Lianna Pottgen, 11/2/22
Calender Display Frontend in Product detail | **Given** I am logged in **when** select a valid reservation **then** I expect to have the option to make the reservation |  |  | Pass | Michael Oldziej, The user should be able to change the starting date so that if they accidentally choose a wrong date they can reselect. 11/2/2022
| **Given** I am logged in **when** I try to select a invalid reservation **then** I expect to not be able to select that date range. |  |  | Pass | Michael Oldziej, 11/7/22
| **Given** I have select a reservation **when** I try to select another date range **then** I should be able to start with a fresh date range to choose. |  |  | Pass | Michael Oldziej, 11/7/22
Buyer, see future campsite availbility | **Given** I am logged in as a buyer **when** I go to look at possible campsites **then** I expect to be able to see the time frame that I could possibly reserve this site. |  |  | Pass | Kolbe Yang, 11/7/22
Buyer see map/browse | **Given** the campsite or location exists **when** I look at the map **then** I expect to see the campsite |  |  | Pass | Kolbe Yang, 11/7/22
Owner, Manage a campsite's reservations in Product Detail | **Given** I am an owner, **When** I click on a campsite **Then** I should see the campsite details and all the associated reservations. |  |  | Pass | Lianna Pottgen 11/7/22
Separate purchased reservations into upcoming and past | **Given** I am logged in as a user**when** I visit the reservations page **then** I expect to clearly see which reservations are upcoming and which are past. |  |  | Pass | Sherry Robinson, 11/07/2022
Store session token in local/session storage | **Given** I am logged in **when** I reload the page**then** I expect to still be logged in |  |  | Pass | Lianna Pottgen 11/7/22
Route homepage to browse when user is logged in | Given I am logged in, when I click "get started" on the home page, Then I should be routed to the browse page. |  |  | Pass | Kolbe Yang, 11/7/22
Buyer route to success page after reservation is created | **Given** I'm a valid logged-in buyer **when** I create a reservation **then** I to be routed to a page stating the reservation has been created. |  |  | Pass | Kolbe Yang, 11/7/22
Owner Route to success page after campsite is deleted | **Given** I'm logged in as admin **when** I delete a campsite **then** I expect to be routed to a page stating that the campsite was successfully deleted. |  |  | Pass | Sherry Robinson, 11/07/2022
campsite description | **Given** the product exists **when** the product description/price is edited by the owner **then** the product is successfully updated with the new information on the E-store website |  |  | Pass | Kolbe Yang, 11/7/22
Display cents for nightly rates | **Given** I'm creating a new campsite **when** I set the rate of the campsite in cents **then** I expect all user purchases to include cents. |  |  | Pass | Sherry Robinson, 11/07/2022